CashLine ERP

MVP Production Project Charter

Controlled Production MVP Implementation, Deployment, Testing, Hosting, Backup, CPM, And Critical Path Governance

| Document Field | Value |
| --- | --- |
| Version | 1.0 - Branded Executive Project Charter |
| Document Date | 2026-04-20 |
| Redesigned | 2026-04-20 |
| Project Sponsor | Khalid Gabr |
| Project Manager | Mostafa El Shahawy |
| Technical Lead | Nour Elsiminy |
| Business Analysis | Doaa Sabry |
| Planned Start | Tuesday, 21 Apr 2026 |
| Planned Finish | Wednesday, 03 Jun 2026 |
| Critical Path Duration | 32 business days from approved start |
| Typography | Tajawal |

Confidential - Prepared for CashLine ERP MVP production governance and project authorization.

# Document Control

| Control Item | Description |
| --- | --- |
| Purpose | Authorize and govern the CashLine ERP controlled production MVP implementation using a professional charter format. |
| Scope | Production MVP, testing, deployment, staging, hosting, backup/recovery, project governance, CPM, dependency nodes, critical path calculation, cost placeholders, and approval matrix. |
| Source Reference | Project Charter - Cashline ERP Implementation.xlsx used as sample structure only. |
| Release Path | Development -> QA -> Staging/Pre-production -> Controlled Production MVP -> Stabilization -> Wider rollout |

## 1. Project Identification

| Field | Value |
| --- | --- |
| Project title | CashLine ERP Controlled Production MVP Implementation |
| Project sponsor | Khalid Gabr |
| Project manager | Mostafa El Shahawy |
| Technical lead | Nour Elsiminy |
| Business analysis | Doaa Sabry |
| Project customer | SMEs, business owners, key users, supplier users, customer users, internal operations users, administrators, and system owner |
| Planned release model | Controlled Production MVP |
| Planned project start date | Tuesday, 21 Apr 2026 |
| Planned project finish date | Wednesday, 03 Jun 2026 |
| CPM calendar basis | 32 business days using Sunday-Thursday working week |
| Recommended release path | Development -> QA -> Staging/Pre-production -> Controlled Production MVP -> Stabilization -> Wider rollout |
| Hosting recommendation | Cloudflare Pages / DNS / WAF -> Azure App Service or Azure Container Apps -> Azure SQL Database -> Azure Blob Storage -> Azure Monitor |
| Planned CPM duration | 32 business days from approved start |

## 2. Project Purpose

The purpose of this project is to prepare, validate, deploy, and stabilize the CashLine ERP platform as a controlled production MVP. The project will move the system from implementation and UAT readiness into a governed production operating model with controlled users, production hosting, staging validation, deployment discipline, database loading controls, backup/recovery safeguards, role-based access, reporting/export readiness, and hypercare support.

The MVP production launch must present CashLine as a credible operational platform while avoiding uncontrolled big-bang go-live risk. The project will support initial production usage, capture stabilization feedback, protect data quality, and prepare the foundation for wider rollout and future module activation.

## 3. Business Objectives

| Objective | Description |
| --- | --- |
| Controlled production activation | Launch CashLine ERP as a limited, governed production MVP for approved users |
| Production credibility | Ensure the platform appears and behaves as a live operational system, not a demo or UAT prototype |
| Workflow continuity | Validate that user actions drive downstream workflow, notification, audit, and reporting effects |
| Access governance | Enforce System Owner, Administrator, supplier, customer, and internal role restrictions |
| Deployment discipline | Establish Development, QA, Staging/Pre-production, Production MVP, Stabilization, and Wider rollout controls |
| Hosting readiness | Implement a reliable and cost-efficient hosting model using Cloudflare and Azure |
| Backup/recovery readiness | Separate production runtime from backup/recovery capability and prove restore readiness |
| Test completion | Execute functional, API, UI, role, workflow, database, desktop, reporting, negative, and smoke testing |
| Stabilization | Operate hypercare after go-live and resolve production-impacting findings |
| Wider rollout readiness | Confirm whether the MVP can expand to more users, functions, clients, and transaction volume |

## 4. Project Scope

### 4.1 In Scope

| Scope Area | Included Work |
| --- | --- |
| Production MVP planning | Finalize release gates, approval criteria, environment strategy, and deployment path |
| Hosting setup | Prepare Cloudflare and Azure target hosting model for frontend, backend, SQL database, storage, and monitoring |
| Staging/pre-production | Create a production-like validation environment before production deployment |
| Production environment | Prepare clean production configuration, database, users, role/function governance, and monitoring |
| Backup/recovery | Define and validate database backups, pre-release backups, document storage protection, release archives, and restore drills |
| CI/CD and release pipeline | Establish controlled build, deployment, validation, and approval flow |
| Database preparation | Apply migrations, reference data, seed data, production-safe configuration, and test-load rules |
| System testing | Execute full MVP test coverage across user journeys, API, workflow, permissions, reports, exports, and desktop parity |
| User governance | Validate System Owner and Administrator behavior, including user/function administration |
| Supplier/customer MVP journeys | Validate onboarding, profile activation, document flow, status, notifications, and reporting impact |
| Internal operations MVP journeys | Validate review, approval, rejection, return, hold, reopen, and audit behavior |
| Reporting and exports | Validate MVP reports and PDF/Excel export capability |
| Desktop parity | Confirm desktop app behavior matches web environment rules |
| Hypercare | Monitor production usage, triage issues, and report stabilization status |

### 4.2 Out Of Scope

| Excluded Area | Notes |
| --- | --- |
| Full enterprise go-live | This charter covers controlled MVP production only |
| Full Islamic Finance production launch | Remains conditional until scoring, Shariah, lender, settlement, and regulatory controls are completed |
| Automated credit decisioning | Not part of MVP production cutover |
| Live iScore or external bureau integration | Future work subject to official membership, access, consent, and legal approval |
| Oracle production parity | Not included unless separately approved |
| Unqualified payment/tax authority live integrations | External integrations must pass owner qualification before activation |
| Broad public user rollout | Wider rollout follows stabilization sign-off |
| Major feature redesign during MVP cutover | Change requests must go through release governance |

## 5. Key Deliverables

| Deliverable | Description | Owner |
| --- | --- | --- |
| Approved MVP production charter | Formal project governance document | Project Manager |
| MVP production deployment plan | Environment, deployment, database, staging, cutover, rollback, and hypercare strategy | Project Manager / Technical Lead |
| Hosting and cost strategy | Cloudflare + Azure hosting recommendation and cost estimate | Technical Lead |
| Production environment configuration | Production-safe runtime configuration and access model | Technical Lead |
| Staging environment | Production-like rehearsal environment | Technical Lead |
| Database migration package | Versioned database migration and seed/reference data plan | Technical Lead |
| Test data pack | Repeatable QA/staging test data | QA / Business Analysis |
| UAT execution evidence | Signed-off MVP journey validation | Business Analysis / QA |
| API and workflow regression evidence | Backend/API workflow validation | Technical Lead / QA |
| Role and access-control validation | System Owner, Administrator, supplier, customer, and internal user enforcement | QA / Technical Lead |
| Backup and restore evidence | Proof of backup creation and restore drill | Technical Lead |
| Production cutover record | Deployment steps, timestamps, approvers, and smoke-test results | Project Manager |
| Hypercare report | Stabilization findings, open issues, actions, and wider-rollout recommendation | Project Manager / Technical Lead |

## 6. Stakeholders And Team

| Stakeholder / Team | Role | Responsibilities |
| --- | --- | --- |
| Khalid Gabr | Project Sponsor / Executive Owner | Business scope approval, financial governance, release authority, strategic direction, final go-live decision |
| Mostafa El Shahawy | Project Manager | Project planning, coordination, timeline tracking, risk management, stakeholder communication, release governance |
| Nour Elsiminy | Technical Lead | Technical solution readiness, hosting, deployment, database, performance, security, bug fixing, production support |
| Doaa Sabry | Business Analysis | Business requirements validation, user journey mapping, UAT coordination, documentation, sign-off support |
| Founders | Executive Leadership | ROI, brand reputation, long-term scalability, commercial credibility |
| Technical team | Technical Support / Engineering | System setup, implementation, bug fixing, performance optimization, release support |
| Implementation team | Customer Service / Enablement | User onboarding, training, support, go-live assistance |
| Client stakeholders | End users / key users | Requirements confirmation, test execution, feedback, acceptance |
| Marketing and Sales | Growth | Convert MVP readiness into client-facing confidence, pipeline support, sales enablement |

## 7. Business Visit Plan

The following business visit plan has been added from the attached workbook: Business Trip Plan for CashLine_ERP.xlsx. It is included as a client/business engagement reference to support MVP production rollout preparation, stakeholder meetings, field readiness, onboarding coordination, and commercial follow-up planning.

### 7.1 Travel Plan A

| Governorate | Travel Date | Travel Day | Departure Date | Departure Day |
| --- | --- | --- | --- | --- |
| Beni Suef | 02 May 2026 | Saturday | 05 May 2026 | Tuesday |
| Minya | 05 May 2026 | Tuesday | 08 May 2026 | Friday |
| Assiut | 08 May 2026 | Friday | 12 May 2026 | Tuesday |
| Sohag | 12 May 2026 | Tuesday | 15 May 2026 | Friday |
| Qena | 15 May 2026 | Friday | 19 May 2026 | Tuesday |
| Luxor | After Eid al-Adha |  |  |  |
| Aswan |  |  |  |  |
| Hurghada |  |  |  |  |

### 7.2 Travel Plan B

| Governorate | Travel Date | Travel Day | Departure Date | Departure Day |
| --- | --- | --- | --- | --- |
| Hurghada | 02 May 2026 | Saturday | 05 May 2026 | Tuesday |
| Qena | 05 May 2026 | Tuesday | 08 May 2026 | Friday |
| Assiut | 08 May 2026 | Friday | 12 May 2026 | Tuesday |
| Sohag | 12 May 2026 | Tuesday | 15 May 2026 | Friday |
| Minya | 15 May 2026 | Friday | 19 May 2026 | Tuesday |
| Luxor | After Eid al-Adha |  |  |  |
| Aswan |  |  |  |  |
| Beni Suef |  |  |  |  |

### 7.3 Visit Plan Governance Notes

| Governance Item | Requirement |
| --- | --- |
| Purpose | Support MVP production rollout, stakeholder engagement, onboarding readiness, commercial validation, and user feedback collection |
| Alignment | Visits should be aligned with staging/UAT, production activation, hypercare, and wider-rollout readiness milestones |
| Output | Each visit should produce meeting notes, user feedback, issues, opportunities, and action owners |
| Project control | Visit outcomes that affect scope, cost, timeline, or production readiness must go through project change governance |
| Data control | No live production data should be collected or shared during visits unless approved by project governance and applicable data policy |

## 8. Governance Model

| Governance Area | Required Control |
| --- | --- |
| Project approval | Sponsor and project manager approval before production execution |
| Scope control | MVP scope freeze before staging promotion |
| Change control | Any major scope or release change requires sponsor/project manager approval |
| Environment control | Production, staging, QA, and development must remain separated |
| Access control | Production access limited to approved users and roles |
| Data control | No UAT/demo/sample records in production |
| Deployment approval | Staging sign-off required before production cutover |
| Backup approval | Pre-release backup required before production deployment |
| Release evidence | Cutover, smoke test, rollback readiness, and hypercare records must be retained |

## 9. High-Level Requirements

| Requirement Area | Requirement |
| --- | --- |
| Production hosting | Host frontend through Cloudflare and backend/database/storage/monitoring through Azure |
| Security | Enforce HTTPS, role-based access, secret management, and no public debug exposure |
| Database | Use versioned migrations, clean production seed data, and production-only transactional data |
| Backup | Separate production runtime from backup/recovery and prove restore capability |
| Testing | Complete QA, staging, UAT, API, workflow, UI, desktop, negative, and smoke testing |
| Reporting | Support MVP operational reports and PDF/Excel exports |
| Desktop | Confirm desktop app inherits the production web/backend behavior |
| Arabic/English | Maintain production-ready UI language behavior |
| Documentation | Maintain deployment, hosting, testing, backup, and project-governance documentation |

## 10. Work Breakdown Structure

| WBS | Workstream | Key Activities |
| --- | --- | --- |
| 1.0 | Project governance | Charter approval, scope freeze, stakeholder alignment, release authority |
| 2.0 | Hosting and infrastructure | Cloudflare setup, Azure backend, Azure SQL, Blob Storage, monitoring, budget alerts |
| 3.0 | Deployment pipeline | Build, package, environment config, CI/CD, release approvals |
| 4.0 | Database and data loading | Migration baseline, seed/reference data, production data rules, test data pack |
| 5.0 | Testing and QA | Functional, API, workflow, UI, desktop, role, negative, reporting, export, smoke testing |
| 6.0 | Staging/UAT | Production-like rehearsal, user acceptance, business sign-off |
| 7.0 | Production cutover | Backup, deployment, migration, configuration, smoke test, activation |
| 8.0 | Hypercare and stabilization | Monitoring, support, issue management, stabilization reporting |
| 9.0 | Wider rollout decision | Go/no-go for broader release based on stabilization evidence |

## 11. CPM Network And Dependency Nodes

The CPM model below uses business-day durations and assumes the project starts on Tuesday, 21 Apr 2026. The schedule uses a Sunday-Thursday working week for business-day calculation.

| Node | Activity | Duration (Days) | Dependencies | Planned Start | Planned Finish |
| --- | --- | --- | --- | --- | --- |
| A | Project charter approval and governance kickoff | 1 | None | 21 Apr 2026 | 21 Apr 2026 |
| B | MVP scope freeze and release baseline confirmation | 2 | A | 22 Apr 2026 | 23 Apr 2026 |
| C | Hosting account, Cloudflare, Azure, DNS, and environment provisioning | 3 | B | 26 Apr 2026 | 28 Apr 2026 |
| D | Backup/recovery model and restore-drill plan | 2 | B | 26 Apr 2026 | 27 Apr 2026 |
| E | CI/CD pipeline and deployment package preparation | 3 | B | 26 Apr 2026 | 28 Apr 2026 |
| F | Database migration, seed, and production data-load preparation | 3 | B | 26 Apr 2026 | 28 Apr 2026 |
| G | QA/staging test-data pack preparation | 2 | B | 26 Apr 2026 | 27 Apr 2026 |
| H | QA system, API, workflow, UI, desktop, and reporting regression | 5 | E, F, G | 29 Apr 2026 | 05 May 2026 |
| I | Security, role, function, and access-control review | 3 | C, E, F | 29 Apr 2026 | 03 May 2026 |
| J | Staging/pre-production deployment rehearsal | 2 | C, D, E, F, H, I | 06 May 2026 | 07 May 2026 |
| K | Staging UAT and business sign-off | 4 | J | 10 May 2026 | 13 May 2026 |
| L | Production readiness gate and go/no-go approval | 1 | K | 14 May 2026 | 14 May 2026 |
| M | Production backup and cutover preparation | 1 | L | 17 May 2026 | 17 May 2026 |
| N | Production deployment and database migration | 1 | M | 18 May 2026 | 18 May 2026 |
| O | Production smoke test and MVP user activation | 1 | N | 19 May 2026 | 19 May 2026 |
| P | Hypercare stabilization window | 10 | O | 20 May 2026 | 02 Jun 2026 |
| Q | Wider rollout decision and closure report | 1 | P | 03 Jun 2026 | 03 Jun 2026 |

## 12. Critical Path Calculation

| Node | Duration | ES | EF | LS | LF | Float | Critical | Planned Start | Planned Finish |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | 1 | 0 | 1 | 0 | 1 | 0 | Yes | 21 Apr 2026 | 21 Apr 2026 |
| B | 2 | 1 | 3 | 1 | 3 | 0 | Yes | 22 Apr 2026 | 23 Apr 2026 |
| C | 3 | 3 | 6 | 5 | 8 | 2 | No | 26 Apr 2026 | 28 Apr 2026 |
| D | 2 | 3 | 5 | 9 | 11 | 6 | No | 26 Apr 2026 | 27 Apr 2026 |
| E | 3 | 3 | 6 | 3 | 6 | 0 | Yes | 26 Apr 2026 | 28 Apr 2026 |
| F | 3 | 3 | 6 | 3 | 6 | 0 | Yes | 26 Apr 2026 | 28 Apr 2026 |
| G | 2 | 3 | 5 | 4 | 6 | 1 | No | 26 Apr 2026 | 27 Apr 2026 |
| H | 5 | 6 | 11 | 6 | 11 | 0 | Yes | 29 Apr 2026 | 05 May 2026 |
| I | 3 | 6 | 9 | 8 | 11 | 2 | No | 29 Apr 2026 | 03 May 2026 |
| J | 2 | 11 | 13 | 11 | 13 | 0 | Yes | 06 May 2026 | 07 May 2026 |
| K | 4 | 13 | 17 | 13 | 17 | 0 | Yes | 10 May 2026 | 13 May 2026 |
| L | 1 | 17 | 18 | 17 | 18 | 0 | Yes | 14 May 2026 | 14 May 2026 |
| M | 1 | 18 | 19 | 18 | 19 | 0 | Yes | 17 May 2026 | 17 May 2026 |
| N | 1 | 19 | 20 | 19 | 20 | 0 | Yes | 18 May 2026 | 18 May 2026 |
| O | 1 | 20 | 21 | 20 | 21 | 0 | Yes | 19 May 2026 | 19 May 2026 |
| P | 10 | 21 | 31 | 21 | 31 | 0 | Yes | 20 May 2026 | 02 Jun 2026 |
| Q | 1 | 31 | 32 | 31 | 32 | 0 | Yes | 03 Jun 2026 | 03 Jun 2026 |

Critical path:

A -> B -> E/F -> H -> J -> K -> L -> M -> N -> O -> P -> Q

Total critical path duration:

32 business days, from Tuesday 21 Apr 2026 to Wednesday 03 Jun 2026

Notes:

• Nodes E and F are parallel critical predecessors to H.

• Node G has one day of float.

• Node C and I have limited float but must not slip beyond their late dates because they affect staging readiness.

• Node D has six days of float but must be complete before staging deployment rehearsal.

## 13. Milestones

| Milestone | Related Nodes | Acceptance Criteria |
| --- | --- | --- |
| Charter approved | A | Sponsor and project manager approval captured |
| MVP scope frozen | B | Scope, exclusions, release baseline, and success criteria confirmed |
| Hosting ready | C | Cloudflare/Azure environment path confirmed and accessible |
| Backup/recovery ready | D | Backup rules, restore drill, RPO/RTO, and owners defined |
| Pipeline ready | E | Build/deploy package is repeatable |
| Database ready | F | Migration and production data-load rules validated |
| QA ready | G | Test-data pack available |
| QA regression complete | H | System, API, workflow, UI, desktop, role, and report tests completed |
| Security/access complete | I | Role/function restrictions validated |
| Staging deployed | J | Production-like deployment rehearsal complete |
| UAT signed off | K | Business confirms staging readiness |
| Production go/no-go approved | L | Release owner approves cutover |
| Production deployed | N | Backend, frontend, DB, storage, config, and desktop path deployed |
| Production smoke passed | O | Critical paths pass in production |
| Hypercare complete | P | Critical issues closed or controlled |
| Wider rollout decision | Q | Executive decision recorded |

## 14. Testing Strategy

| Test Type | Coverage |
| --- | --- |
| Functional UAT | Supplier, customer, internal operations, administrator, and system owner journeys |
| API testing | Request/response validation, error behavior, authorization, and workflow-triggered API behavior |
| Workflow testing | Approval, rejection, return, hold, reopen, activation, and status progression |
| Database testing | Migration, seed data, test loading, production data rules, and rollback readiness |
| Role/permission testing | Sidebar, function access, backend enforcement, unauthorized route denial |
| UI/UX testing | Layout, buttons, navigation, Arabic/English behavior, desktop parity, and production content cleanup |
| Reporting testing | Dashboard, reports, drilldowns, PDF export, Excel export, and audit visibility |
| Negative testing | Invalid data, duplicate actions, unauthorized access, missing mandatory reasons, and invalid state transitions |
| Asynchronous testing | Notifications, retries, failures, recovery, and delayed workflow effects |
| Production smoke testing | Login, role visibility, one supplier/customer/internal path, reports, exports, and health checks |

## 15. Deployment Strategy

The deployment strategy follows the approved release path:

Development -> QA -> Staging/Pre-production -> Controlled Production MVP -> Stabilization -> Wider rollout

Deployment rules:

• No direct production change without staging rehearsal.

• No production deployment without pre-release backup.

• No UAT/demo records in production.

• No production launch without role/access validation.

• No wider rollout before stabilization sign-off.

• All release actions must be recorded in the production cutover record.

## 16. Hosting Strategy

| Layer | MVP Recommendation |
| --- | --- |
| Frontend | Cloudflare Pages |
| DNS / CDN / WAF | Cloudflare |
| Backend API | Azure App Service or Azure Container Apps |
| Database | Azure SQL Database |
| Documents and exports | Azure Blob Storage |
| Monitoring | Azure Application Insights and Azure Monitor |
| Secrets/configuration | Azure Key Vault or Azure App Configuration |
| Backup/recovery | Azure SQL PITR, pre-release backup, Blob soft-delete/versioning, release package archive |

## 17. Backup And Recovery Strategy

Production and backup/recovery must remain separate.

| Backup Area | MVP Requirement |
| --- | --- |
| Azure SQL automatic backups | Enable point-in-time restore with at least 7 days minimum retention, preferably up to 35 days if budget allows |
| Pre-deployment backup | Required before every production deployment or migration |
| Blob/document protection | Enable soft-delete, versioning, or equivalent retention |
| Release package archive | Preserve backend, frontend, desktop, Cloudflare, and configuration package |
| Restore drill | Run before go-live and monthly during MVP stabilization |
| RPO | MVP baseline: 24 hours or better unless live finance data requires tighter recovery |
| RTO | MVP baseline: same business day recovery unless business requires tighter SLA |

## 18. Budget Framework

Hosting cost is included based on the approved hosting strategy. Other cost elements are intentionally left blank for business/finance completion.

| Cost Element | Estimated Cost | Notes |
| --- | --- | --- |
| Hosting - Lean controlled MVP | $80 - $250/month | Cloudflare + Azure low-cost controlled MVP |
| Hosting - Production-comfortable MVP | $250 - $600/month | Cloudflare + Azure with more production comfort |
| Human resources |  | To be completed by business/finance |
| Implementation services |  | To be completed by business/finance |
| QA/testing services |  | To be completed by business/finance |
| Security review |  | To be completed by business/finance |
| Training and enablement |  | To be completed by business/finance |
| Support and operations |  | To be completed by business/finance |
| Marketing and sales |  | To be completed by business/finance |
| Contingency |  | To be completed by business/finance |
| Total |  | To be completed by business/finance |

## 19. Risks And Mitigations

| Risk | Impact | Mitigation | Owner |
| --- | --- | --- | --- |
| User adoption resistance | Slow uptake and weak MVP value perception | Training, role-based walkthroughs, hypercare support | Implementation team |
| Production data contamination | Loss of production credibility and reporting quality | No UAT/demo data in production; controlled data load checklist | Technical Lead |
| Migration failure | Deployment delay or data inconsistency | Migration dry-run, backup, rollback plan | Technical Lead |
| Role/access misconfiguration | Unauthorized access or hidden function failure | Role/function regression testing and production smoke validation | QA / Technical Lead |
| Hosting instability | Downtime or poor user experience | Cloudflare + Azure managed services, monitoring, alerts | Technical Lead |
| Backup not restorable | Recovery failure during incident | Restore drill before go-live and monthly checks | Technical Lead |
| Unclear scope changes | Schedule delay and project drift | Scope freeze, change approval, sponsor escalation | Project Manager |
| Critical bugs after go-live | User disruption and reputational risk | Hypercare, severity triage, rollback readiness | Project Manager / Technical Lead |
| Integration assumptions | False readiness claims | Keep unqualified integrations disabled until owner sign-off | Project Sponsor / Technical Lead |
| ETA/e-invoicing, Fawry, or Paymob activated by third party during MVP | Scope, schedule, security, testing, reconciliation, tax, and release risk if credentials become active unexpectedly | Treat as go-live uncertainty path; require change control, staging test, owner sign-off, rollback plan, and production release approval | Project Sponsor / Project Manager / Technical Lead |

## 20. External Integration Go-Live Uncertainty Paths

ETA/e-invoicing, Fawry, and Paymob are explicit go-live uncertainty paths for the MVP. They are held/conditional until third-party credentials, merchant/account access, authority access, endpoint configuration, callback readiness, certification evidence, and owner sign-off are available.

These paths may be added to the controlled MVP at any time if ETA, Fawry, or Paymob activate the required credentials or access during MVP preparation, staging, cutover, stabilization, or early production. This should be read as a project risk and conditional activation path, not as a permanent exclusion.

| External Path | Current MVP Position | Trigger For Activation | Required Governance |
| --- | --- | --- | --- |
| ETA / e-invoicing | Held / conditional | ETA credentials, authority access, target endpoint, and submission evidence become available | Change request, staging submission test, tax/finance sign-off, rollback plan, production approval |
| Fawry | Held / conditional | Merchant credentials, API access, callback configuration, and payment test evidence become available | Change request, payment-flow test, reconciliation check, rollback plan, production approval |
| Paymob | Held / conditional | Merchant credentials, API access, callback configuration, and payment test evidence become available | Change request, payment-flow test, reconciliation check, rollback plan, production approval |

No activation should occur directly in production only because credentials become available. Activation requires impact assessment, security review, staging/pre-production validation, owner sign-off, and release evidence.

## 21. Success Criteria

| Success Criterion | Measurement |
| --- | --- |
| Production MVP is live | Approved users can access production environment |
| No critical production blockers | Severity 1 issues are zero or controlled by approved workaround |
| Role governance works | System Owner, Administrator, supplier, customer, and internal role visibility is enforced |
| Core workflows operate | Supplier/customer onboarding and internal review workflows complete as designed |
| Reports and exports work | MVP reports export successfully to PDF/Excel |
| Backup/recovery is proven | Pre-release backup and restore drill evidence exist |
| Hypercare is operating | Daily issue review and stabilization reporting active |
| Wider rollout decision ready | Sponsor receives evidence-based go/no-go recommendation |

## 22. Constraints And Assumptions

| Type | Item |
| --- | --- |
| Constraint | Limited initial resources and controlled MVP budget |
| Constraint | Production launch must not include demo/UAT content |
| Constraint | Islamic Finance production activation remains conditional |
| Constraint | Wider rollout depends on stabilization evidence |
| Assumption | Cloudflare and Azure are acceptable hosting platforms for MVP |
| Assumption | SQL Server/Azure SQL remains the preferred production database path |
| Assumption | Team names from the source charter represent real project roles |
| Assumption | Non-hosting costs will be completed separately by business/finance |

## 23. Approval Matrix

| Approval Role | Name | Approval Status | Signature / Date |
| --- | --- | --- | --- |
| Project Sponsor | Khalid Gabr | Pending |  |
| Project Manager | Mostafa El Shahawy | Pending |  |
| Technical Lead | Nour Elsiminy | Pending |  |
| Business Analysis | Doaa Sabry | Pending |  |
| Client / Business Representative |  | Pending |  |

## 24. Final Charter Statement

This charter authorizes the CashLine ERP team to proceed with controlled production MVP preparation, validation, deployment, and stabilization under the governance, scope, timeline, dependencies, hosting strategy, testing requirements, backup/recovery controls, and success criteria defined in this document.

The project should not be treated as a full enterprise go-live. It is a governed MVP production activation designed to prove operational readiness, protect production quality, support early users, and prepare CashLine for wider rollout after stabilization evidence is reviewed and approved.