## Deep Cases
Execution Type | Execution Date | Prepared By | Overall Outcome | Note
Deep Functional Test Design Baseline | 2026-04-11 | Codex | Ready For Execution | Prepared from the current CashLine implementation, API/UAT evidence, workflow validation, onboarding controls, frontend segregation, and desktop/browser parity baseline.
List Item
Each case validates one primary behavior or one tightly related behavior set.
Cases cover success path, validation path, blocked path, exception path, permission path, and downstream state effect where relevant.
Where a case depends on visible data propagation, the expected result includes the target downstream screen, queue, status, or log.
These cases are intended to be reusable for regression, defect retest, controlled UAT, and go-live validation.
Test Case ID | Linked Deep Scenario | Module | Title | Preconditions | Steps | Expected Result | Status | Execution Basis | Execution Notes
DFTC-PLT-001 | DFS-PLT-01 | Platform Access | Login from root landing redirects to governed login shell | Public root URL is reachable. | Open root URL. ¦ Observe redirect. ¦ Confirm login shell loads. | Root redirects to the governed login entry and no protected content is exposed pre-login. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-PLT-002 | DFS-PLT-01 | Platform Access | Supplier user lands in supplier package after login | Supplier test account exists and is active. | Open supplier package URL. ¦ Sign in with supplier account. ¦ Observe landing page and navigation. | Supplier user lands inside supplier workspace and does not see internal or customer-only navigation. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-PLT-003 | DFS-PLT-01 | Platform Access | Customer user lands in customer package after login | Customer test account exists and is active. | Open customer package URL. ¦ Sign in with customer account. ¦ Observe landing page and navigation. | Customer user lands inside customer workspace and does not see internal or supplier-only navigation. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-PLT-004 | DFS-PLT-01 | Platform Access | Operations user lands in internal package after login | Operations account exists and is active. | Open internal operations package URL. ¦ Sign in with operations account. ¦ Observe workbench route and menus. | Operations user lands in internal workspace with onboarding, monitoring, and back-office controls visible. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-PLT-005 | DFS-PLT-02 | Platform Access | Desktop app opens the same governed shell and honors package routing | Desktop app is installed and points to the target environment. | Launch desktop app. ¦ Navigate to package URL or sign in via login entry. ¦ Validate post-login route. | Desktop behaves consistently with browser for initial route, login, and post-login package access. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-PLT-006 | DFS-PLT-02 | Platform Access | Desktop logout clears session and returns to login | User is signed in on desktop. | Select logout. ¦ Close desktop app. ¦ Reopen desktop app. | Session is cleared securely and app returns to login without unauthorized reuse of the prior package state. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-PLT-007 | DFS-PLT-03 | Localization | Public landing page renders self-onboarding section in Arabic | Arabic language option is available. | Open login/public landing page. ¦ Switch language to Arabic. ¦ Refresh page if needed. | Self-onboarding labels, buttons, and explanatory text appear in Arabic. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-PLT-008 | DFS-PLT-03 | Localization | Operations onboarding workbench renders Arabic statuses and actions | Operations user can access internal package. | Sign in as Operations. ¦ Switch to Arabic. ¦ Open onboarding workbench. | Case tables, action labels, and workflow-related copy appear in Arabic rather than falling back to English. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-PLT-009 | DFS-PLT-04 | Security | Wrong-role direct package access resets incompatible cached session | A cached session exists for a different role. | With internal session active, open supplier package URL. ¦ Observe route handling. | Incompatible session is cleared or redirected to login; user is not silently admitted into an unauthorized package. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-PLT-010 | DFS-PLT-04 | Security | Protected route without authentication redirects to login with return target | No auth cookie or token is present. | Open protected supplier or internal route directly. ¦ Observe redirect target. | System redirects to login and preserves intended return URL for authorized use after sign-in. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-001 | DFS-ONB-01 | Public Onboarding | Supplier lead capture stores minimal lead and routes to supplier onboarding | Public landing page is available. | Choose Become a Supplier. ¦ Enter email, phone, and company/contact name. ¦ Select Continue Onboarding. | Lead is created, visible to Operations, and browser moves to supplier onboarding path. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-002 | DFS-ONB-01 | Public Onboarding | Customer lead capture stores minimal lead and routes to customer onboarding | Public landing page is available. | Choose Become a Customer. ¦ Enter minimum lead fields. ¦ Select Continue Onboarding. | Lead is created, visible to Operations, and browser moves to customer onboarding path. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-003 | DFS-ONB-02 | Public Onboarding | Supplier self-onboarding saves core profile and KYC data | Supplier prospect is on supplier onboarding page. | Enter supplier company and contact data. ¦ Complete KYC-required fields. ¦ Save or continue through onboarding. | Supplier onboarding data is accepted, persisted, and available for later submission/review. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-004 | DFS-ONB-02 | Public Onboarding | Supplier uploads supported KYC file formats | Supplier onboarding page is open. | Choose upload control. ¦ Upload PDF, JPG, JPEG, or PNG evidence. ¦ Complete upload. | Supported files upload successfully and return governed storage references for onboarding. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-005 | DFS-ONB-02 | Public Onboarding | Supplier submission creates public self-initiated onboarding case | Supplier onboarding data and required documents are present. | Submit supplier onboarding package. ¦ Open operations workbench as internal user. ¦ Locate resulting case. | System creates supplier onboarding case with PUBLIC_SELF_INITIATED path and linked lead reference. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-006 | DFS-ONB-02 | Public Onboarding | Supplier remains restricted to onboarding-only behavior before activation | Supplier prospect has submitted onboarding but is not activated. | Attempt to access supplier operational features before activation. ¦ Observe visibility and access control. | Non-onboarding features remain hidden, disabled, or blocked until activation completes. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-007 | DFS-ONB-03 | Public Onboarding | Customer self-onboarding saves core profile and KYC data | Customer prospect is on customer onboarding page. | Enter customer company and contact data. ¦ Complete KYC-required fields. ¦ Save or continue through onboarding. | Customer onboarding data is accepted, persisted, and available for later submission/review. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-008 | DFS-ONB-03 | Public Onboarding | Customer uploads supported KYC file formats | Customer onboarding page is open. | Choose upload control. ¦ Upload PDF, JPG, JPEG, or PNG evidence. ¦ Complete upload. | Supported files upload successfully and return governed storage references for onboarding. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-009 | DFS-ONB-03 | Public Onboarding | Customer submission creates public self-initiated onboarding case | Customer onboarding data and required documents are present. | Submit customer onboarding package. ¦ Open operations workbench. ¦ Locate resulting case. | System creates customer onboarding case with PUBLIC_SELF_INITIATED path and linked lead reference. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-010 | DFS-ONB-04 | Operations Onboarding | Operations creates supplier onboarding case manually | Operations user is signed in to internal package. | Open onboarding workbench. ¦ Choose Create Supplier Onboarding Case. ¦ Enter minimum supplier details and save. | Supplier case is created with INTERNAL_MANUAL initiation path and governed review status. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-011 | DFS-ONB-04 | Operations Onboarding | Operations creates customer onboarding case manually | Operations user is signed in to internal package. | Open onboarding workbench. ¦ Choose Create Customer Onboarding Case. ¦ Enter minimum customer details and save. | Customer case is created with INTERNAL_MANUAL initiation path and governed review status. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-012 | DFS-ONB-05 | Operations Onboarding | Operations approves compliant onboarding case | Selected case has satisfied checklist and prerequisite rules. | Select onboarding case. ¦ Choose Approve action. ¦ Observe case and profile state. | Approval succeeds, status changes are stored, and downstream activation path becomes available. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-013 | DFS-ONB-05 | Operations Onboarding | Operations returns onboarding case for rework with notes | Case is under review. | Select case. ¦ Choose Return for Rework. ¦ Enter notes and submit. | Case moves to returned state, notes are stored, and applicant/operations workbench reflects the exception path. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-014 | DFS-ONB-05 | Operations Onboarding | Operations rejects onboarding case with rejection notes | Case is under review. | Select case. ¦ Choose Reject. ¦ Enter rejection notes and submit. | Case moves to rejected state, reason is stored, and approval/activation is blocked. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-015 | DFS-ONB-05 | Operations Onboarding | Operations places onboarding case on hold | Case is under review. | Select case. ¦ Choose Hold. ¦ Enter hold reason. | Case moves to ON_HOLD state with hold reason and queue visibility updated. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-016 | DFS-ONB-05 | Operations Onboarding | Operations reopens held onboarding case | Case is currently on hold. | Select held case. ¦ Choose Reopen. ¦ Enter reopen note if required. | Case exits hold state and returns to governed working status with audit trace preserved. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-017 | DFS-ONB-05 | Operations Onboarding | Operations activates approved onboarding case and provisions access | Case has been approved and prerequisites are satisfied. | Open approved case. ¦ Run activation action. ¦ Verify resulting access state. | Profile is activated, activation audit fields are stored, and onboarding access provisioning/credential queue is triggered. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-018 | DFS-ONB-06 | KYC | Approval is blocked when required checklist items remain unresolved | Case has at least one unresolved required checklist item. | Attempt approval. ¦ Observe business-rule response. | Approval is blocked with clear error and case remains in governed pre-approval state. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-019 | DFS-ONB-06 | KYC | Approval is blocked when open findings exist | Case has active blocking review findings. | Attempt approval. ¦ Observe business-rule response. | Approval is blocked until findings are resolved or cleared under governance. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-ONB-020 | DFS-ONB-06 | KYC | Unsupported KYC file type is rejected | Uploader is available. | Attempt to upload unsupported file type such as EXE or unsupported document. ¦ Observe response. | System rejects the upload with validation error and no document is recorded. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-SUP-001 | DFS-SUP-01 | Supplier Frontend | Supplier package shows supplier-only navigation set | Supplier account is active. | Sign in as supplier. ¦ Review main navigation and visible sections. | Supplier sees supplier-facing sections only, including status, onboarding, financing interactions, and payments UI visibility where relevant. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-SUP-002 | DFS-SUP-01 | Supplier Frontend | Supplier cannot access internal-only route from supplier package | Supplier is signed in. | Attempt direct navigation to internal route. ¦ Observe result. | Access is denied or redirected; no internal controls are exposed. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-SUP-003 | DFS-SUP-01 | Supplier Frontend | Supplier sees payments section as UI-only future-ready feature | Supplier package is loaded. | Open supplier workspace. ¦ Locate payments section. | Payments section appears in UI but does not falsely claim live provider closure when held conditions apply. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-CUS-001 | DFS-CUS-01 | Customer Frontend | Customer package shows customer-only navigation set | Customer account is active. | Sign in as customer. ¦ Review main navigation and visible sections. | Customer sees customer-facing sections only, including onboarding, requests, financing interactions, and payments UI visibility where relevant. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-CUS-002 | DFS-CUS-01 | Customer Frontend | Customer cannot access supplier-only route from customer package | Customer is signed in. | Attempt direct navigation to supplier route. ¦ Observe result. | Access is denied or redirected; no supplier controls are exposed. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-CUS-003 | DFS-CUS-01 | Customer Frontend | Customer sees payments section as UI-only future-ready feature | Customer package is loaded. | Open customer workspace. ¦ Locate payments section. | Payments section appears in UI but remains aligned with held external integration posture. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INT-001 | DFS-INT-01 | Internal Frontend | Operations user sees onboarding workbench and case actions | Operations account is active. | Sign in to internal package. ¦ Open onboarding workbench. ¦ Review action buttons and case detail. | Operations user can access case list, details, and governed actions. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INT-002 | DFS-INT-01 | Internal Frontend | Operations user sees workflow monitoring and exception visibility | Operations account is active. | Open workflow monitoring. ¦ Review live queues, traces, or exception views. | Internal package exposes workflow monitoring and exception visibility without leaking to external packages. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INT-003 | DFS-INT-02 | Internal Frontend | Finance user sees finance-specific controls only | Finance account is active. | Sign in as finance user. ¦ Review visible menus and actions. | Finance package access includes finance-relevant approvals, statements, and payment visibility without operations-only controls. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-P2P-001 | DFS-P2P-01 | Procurement | Purchase requisition create, submit, approve path | Procurement test data is available. | Create requisition. ¦ Submit for approval. ¦ Approve with authorized user. | Requisition status changes correctly and becomes available for downstream RFQ/evaluation actions. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-P2P-002 | DFS-P2P-01 | Procurement | RFQ and quotation evaluation lead to governed purchase order award | Approved requisition exists. | Issue RFQ. ¦ Record supplier quotations. ¦ Evaluate and award PO. | Awarded PO reflects selected quotation with audit trace and downstream purchasing continuity. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-P2P-003 | DFS-P2P-02 | Procurement | Goods receipt creates downstream match and payable readiness | Purchase order exists and is receivable. | Post goods receipt. ¦ Inspect downstream AP/match state. | Receipt updates inventory and payable readiness consistently. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-P2P-004 | DFS-P2P-02 | Procurement | Blocked or disputed supplier flow prevents normal payable continuation | Transaction or supplier is on hold/dispute state. | Attempt normal downstream processing. ¦ Observe block behavior. | Held/disputed state blocks progression until governance releases it. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INV-001 | DFS-INV-01 | Inventory | Inventory adjustment create, approve, and post | Inventory item and warehouse exist. | Create inventory adjustment. ¦ Submit and approve. ¦ Post adjustment. | Adjustment status and quantity impact are recorded with auditability. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INV-002 | DFS-INV-01 | Inventory | Stock count variance workflow records variance for review | Stock count session is prepared. | Capture physical count. ¦ Submit variance. ¦ Review variance path. | Variance is recorded, reviewable, and reflected in stock-control workflow. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INV-003 | DFS-INV-01 | Inventory | Warehouse transfer create, approve, and post | Two valid warehouses exist. | Create transfer. ¦ Approve transfer. ¦ Post transfer. | Transfer updates warehouse balances correctly with traceable lifecycle. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INV-004 | DFS-INV-01 | Inventory | Restricted stock states prevent unrestricted use | Item is placed in quarantine, damaged, or expiry-related state. | Attempt to use restricted stock in normal flow. ¦ Observe result. | System prevents unauthorized consumption of restricted stock and preserves state visibility. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-OTC-001 | DFS-OTC-01 | Sales | Sales order create and submit | Customer and item master data exist. | Create sales order. ¦ Submit order. ¦ Review resulting state. | Order enters governed sales lifecycle and becomes available for downstream dispatch/invoicing. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-OTC-002 | DFS-OTC-01 | Sales | Credit hold blocks order continuation until controlled release | Customer is under credit hold. | Attempt order continuation or release-sensitive step. ¦ Observe result. | Credit hold blocks downstream action until authorized release. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-OTC-003 | DFS-OTC-01 | Sales | Dispatch and proof-of-delivery update operational completion state | Approved order exists and is dispatchable. | Create dispatch. ¦ Record proof of delivery. ¦ Review completion state. | Dispatch and delivery evidence are stored and reflected in downstream sales state. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-OTC-004 | DFS-OTC-01 | Sales | Sales return and credit-note issuance follow governed finance outcome | Completed sale exists. | Create sales return. ¦ Approve/complete return. ¦ Review credit-note outcome. | Return creates governed credit-note or receivable effect according to business rules. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FIN-001 | DFS-FIN-01 | Finance | AR invoice create, approve, and post | Revenue source transaction exists. | Create AR invoice. ¦ Submit/approve. ¦ Post invoice. | AR invoice lifecycle completes with traceable finance effect. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FIN-002 | DFS-FIN-01 | Finance | AR receipt create, approve, post, reverse, and reallocate | Receivable exists. | Create receipt. ¦ Approve and post. ¦ Reverse or reallocate where supported. | Receipt actions are governed and traceable across allocation changes. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FIN-003 | DFS-FIN-01 | Finance | AP bill approval and payment readiness behavior | Goods receipt or AP source exists. | Create or open AP bill. ¦ Approve bill. ¦ Inspect payment readiness state. | AP bill becomes payment-ready only after required approvals and validations. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FIN-004 | DFS-FIN-01 | Finance | Period lock blocks prohibited finance actions | Target period is locked. | Attempt posting or finance action in locked period. ¦ Observe result. | Locked period blocks prohibited action with controlled validation response. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FIN-005 | DFS-FIN-01 | Finance | Close journal create, approve, and post | Close period and journal permissions exist. | Create close journal. ¦ Submit/approve. ¦ Post journal. | Close journal is fully traceable and follows approval discipline. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FIN-006 | DFS-FIN-01 | Finance | Treasury transfer creates governed cash movement visibility | Treasury accounts exist. | Initiate treasury transfer. ¦ Approve/post transfer. ¦ Review resulting cash movement. | Transfer updates treasury state and remains auditable. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FX-001 | DFS-FX-01 | FX | FX quote history is visible for governed decision-making | FX data exists. | Open FX quote history. ¦ Review entries and timestamps. | FX history is visible and usable for review. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FX-002 | DFS-FX-01 | FX | FX manual override preserves governance and audit trail | User has authority to perform governed override. | Apply FX override. ¦ Save action. ¦ Inspect audit trail. | Override is recorded with user, timing, and resulting value trace. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FX-003 | DFS-FX-01 | FX | Revaluation updates finance outputs consistently | FX-sensitive balances exist. | Run revaluation-related flow. ¦ Review resulting finance/report outputs. | Currency-sensitive reporting and finance outcomes reflect governed revaluation logic. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-TAX-001 | DFS-TAX-01 | Tax and Statements | ETA payload preview and validation pack can be reviewed | Tax-ready transaction set exists. | Open ETA/tax preview flow. ¦ Review generated payload/validation surface. | Finance user can inspect generated tax data while external-lane closure remains correctly represented. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-TAX-002 | DFS-TAX-01 | Tax and Statements | Customer statement generation creates governed statement output | Customer ledger/activity exists. | Generate customer statement. ¦ Review output and logs. | Statement is generated and traceable in delivery/logging surfaces. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-TAX-003 | DFS-TAX-01 | Tax and Statements | Supplier statement and reconciliation visibility are available | Supplier finance data exists. | Open supplier statement or reconciliation view. ¦ Review output. | Supplier-facing finance statement data is available and aligned with permissions. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-IF-001 | DFS-IF-01 | Islamic Finance | Partner lender governance lifecycle | Internal financing governance role exists. | Create partner lender. ¦ Submit/approve/activate according to permissions. | Partner lender record follows governed lifecycle and becomes available for financing chain use. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-IF-002 | DFS-IF-01 | Islamic Finance | Product profile and facility governance lifecycle | Financing governance user is active. | Create product profile. ¦ Approve/activate. ¦ Create facility and govern its lifecycle. | Product/facility artifacts follow approval and activation discipline. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-IF-003 | DFS-IF-01 | Islamic Finance | Financing request through Murabaha case progression | Required financing master data exists. | Create financing request. ¦ Process request decisions. ¦ Create/progress Murabaha case. | Request and case chain follows defined governance and state model. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-IF-004 | DFS-IF-01 | Islamic Finance | Disbursement and settlement linkage preserve finance traceability | Murabaha case is approval-ready. | Create and approve disbursement. ¦ Execute disbursement. ¦ Review settlement linkage. | Disbursement and settlement states remain consistent and traceable. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-NOT-001 | DFS-NOT-01 | Notifications | Onboarding activation queues credential notifications | Approved case is ready for activation. | Activate onboarding case. ¦ Inspect notification queue/log. | Credential notification intent is queued and traceable across supported channels. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-NOT-002 | DFS-NOT-01 | Notifications | Notification failure or pending state remains visible for follow-up | Notification orchestration/logging is available. | Inspect outbound notification state after queued action. ¦ Review retry/pending markers. | Operations/support can identify pending or failed communication states for follow-up. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-MON-001 | DFS-MON-01 | Workflow Monitoring | Workflow monitoring shows live case progression | Active workflow items exist. | Open workflow monitoring. ¦ Inspect active items. ¦ Perform action on one case and refresh. | Monitoring view reflects current status progression and user actions in near-real time. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-MON-002 | DFS-MON-01 | Workflow Monitoring | Exception queues surface actionable held or returned cases | Held/returned cases exist. | Open exception or onboarding queues. ¦ Review surfaced items. | Support and operations users can identify and act on exception-state work items. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INTG-001 | DFS-INTG-01 | Integrations | Payments UI is visible while Paymob/Fawry stay held | Frontend package is loaded for relevant role. | Open payments section. ¦ Review UI and messaging. | Payments area appears as designed without misrepresenting provider live closure. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INTG-002 | DFS-INTG-01 | Integrations | ETA surfaces remain available while target-environment closure is held | Tax/ETA workflow is available. | Open ETA/tax area. ¦ Review visible state and controls. | ETA-related UI and process visibility remain available while external qualification is clearly not overstated. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-P2P-005 | DFS-P2P-01 | Procurement | Quotation comparison preserves selected supplier evidence | Multiple quotations exist. | Open evaluation view. ¦ Compare quotations. ¦ Confirm selected supplier evidence. | Selected supplier and supporting comparison evidence are visible and auditable. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-P2P-006 | DFS-P2P-01 | Procurement | Purchase order amendment follows governed status control | Purchase order exists and amendment is allowed. | Edit PO in governed state. ¦ Resubmit for approval if required. ¦ Review audit trail. | Amendment is controlled by status and audit trace. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INV-005 | DFS-INV-01 | Inventory | Inventory negative or invalid quantity input is rejected | Inventory transaction entry is available. | Enter invalid or negative quantity where not allowed. ¦ Submit transaction. | Validation prevents invalid inventory movement and no state corruption occurs. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-INV-006 | DFS-INV-01 | Inventory | Damaged/quarantine stock remains visible in internal monitoring | Restricted stock exists. | Open internal monitoring or inventory views. ¦ Locate restricted stock. | Restricted stock state is visible for operations control and excluded from normal use. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-OTC-005 | DFS-OTC-01 | Sales | Sales invoice reflects source order and dispatch linkage | Completed dispatch exists. | Open generated invoice. ¦ Trace back to order and dispatch. | Invoice traces back correctly to upstream sales events. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-OTC-006 | DFS-OTC-01 | Sales | Customer return path updates AR exposure correctly | Customer return is processed. | Review customer ledger after return/credit outcome. ¦ Confirm finance effect. | Customer receivable exposure reflects governed return/credit logic. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FIN-007 | DFS-FIN-01 | Finance | Operational posting is traceable into GL outputs | AP or AR posting is completed. | Open finance traceability or report view. ¦ Locate posted transaction. | Business transaction is traceable into GL/reporting outputs. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FIN-008 | DFS-FIN-01 | Finance | Reversal path preserves original and reversed document history | Posted finance document exists. | Run allowed reversal. ¦ Inspect history and resulting balances. | Original and reversal records are both retained with correct linkage. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-FIN-009 | DFS-FIN-01 | Finance | Statement export produces usable output for finance user | Statement generation has completed. | Export statement/report. ¦ Open exported artifact. | Export completes successfully and matches current governed data. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-IF-005 | DFS-IF-01 | Islamic Finance | Shariah review attaches recommendation to financing chain | Financing request is awaiting Shariah review. | Open Shariah review step. ¦ Record recommendation. ¦ Save/approve through governed path. | Recommendation is stored and visible in the financing chain. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-IF-006 | DFS-IF-01 | Islamic Finance | Contract generation links supporting Murabaha evidence | Murabaha case has required data. | Generate contract artifacts. ¦ Review linked evidence and schedule. | Contract generation preserves linked asset/evidence context. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-MON-003 | DFS-MON-01 | Workflow Monitoring | Workflow monitoring unauthorized access is denied | No valid internal auth is present. | Attempt direct access to workflow monitoring route. ¦ Observe result. | Route requires proper authentication/authorization and denies external access. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.
DFTC-MON-004 | DFS-MON-01 | Workflow Monitoring | Monitoring view reflects onboarding hold/reopen transition | Case can be placed on hold and reopened. | Hold case. ¦ Refresh monitoring. ¦ Reopen case. ¦ Refresh monitoring again. | Monitoring reflects both hold and reopen state transitions accurately. | READY_FOR_EXECUTION | Detailed functional test design baseline derived from the current CashLine browser, desktop, API, and workflow implementation. | Capture actual result, defect reference, and evidence link during execution.